## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Halan | 29/09/2025 | Streamlit form crashes when 'loan amount' is left blank. | Sprint 1 | Frontend | User Interface | Added default value of 0.0 for optional loan amount fields | 30/09/2025 | Closed | Fixed in validation logic.
2 | Halan | 30/09/2025 | A common failure occurs in one-hot encoding when a category in the test data is unseen during training. | Sprint 1 | Backend | Functional | Updated pipeline to handle unknown categories using 'ignore' or 'mode'. | 2025-02-10 | Closed | Updated preprocessing pipeline.
3 | Halan | 14/10/2025 | Validation accuracy only 72%. | Sprint 2 | ML | Performance | Performed Hyperparameter tuning (max_depth min_samples_split) using GridSearchCV. | 15/10/2025 | Closed | Validation accuracy improved to 80%.
4 | Halan | 22/10/2025 | There is a layout issue where the SHAP dependence plot and the prediction text are displayed on top of each other. | Sprint 3 | Frontend | User Interface | Adjusted Streamlit layout columns and plot dimensions | 25/10/25 | Closed | UI layout fixed.
5 | Halan | 2025-05-11 | Chatbot returns error for valid queries | Sprint 4 | Backend | Functional | Retrained/Fine-tuned NLP intent classifier with more financial data samples | 2025-08-10 | Closed | Model retrained with financial Q&A samples.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others